## Roadmap
October 8, 2026
2027-2029 California ISO Infrastructure Policy Initiatives Roadmap
|  | 2026 | 2027 |  |  |  | 2028 |  |  |  | 2029
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Transmission Planning and MOU Coordination
| Order No. 1920 Implementation | 2027 Q2: Implementation
| Transmission timeline completion | 2026 Q4: Ongoing public dialogue
| MOU update | 2026 Q4: Policy development; 2028 Q1: Implementation
Large Load Interconnection and Study
| Order to Show Cause 205 filing | 2026 Q4: Policy development; 2027 Q3: Decision; 2027 Q4: Implementation
| Consideration of permanent flexible interconnection and proximate loads | 2027 Q1: Policy development; 2027 Q4: Decision; 2028 Q1: Implementation
| Consideration of risk-mitigating curtailment | 2027 Q1: Policy development; 2027 Q4: Decision; 2028 Q1: Implementation
Interconnection Process Enhancements
| IPE 6.0 (Prior to Cluster 17) | 2026 Q4: Policy development; 2027 Q2: Decision; 2027 Q3: Implementation
| IPE 7.0 (if needed) | 2027 Q3: Policy development; 2028 Q2: Decision; 2028 Q3: Implementation
| IPE 8.0 (if needed) | 2028 Q3: Policy development; 2029 Q2: Decision; 2029 Q3: Implementation
Resource Adequacy Modeling and Program Design
| Track 5: MIC enhancements | 2026 Q4: Policy development; 2027 Q3: Decision; 2027 Q4: Implementation
Compensation for reactive power from IBRs outside of specified range |  | 2027 Q1: Public dialogue; 2028 Q1: Policy development
NOTE: All implementation dates listed are "no sooner than"

## Initiative Descriptions
Initiative Descriptions
Transmission Planning |  | The annual transmission plan serves as the formal and Board-approved roadmap for infrastructure requirements for the ISO balancing authority. ISO and participating transmission owner studies demonstrate how the ISO is planning for infrastructure needs while meeting North American Electric Reliability Corporation and ISO planning standards.
| Order No. 1920 Implementation | FERC issued Order No. 1920 on May 13, 2024 to address long-term transmission planning and associated cost allocation processes
| Transmission timeline completion | The ISO works closely with California state agencies, participating transmission owners (PTOs) and industry partners to ensure timely completion of approved transmission projects and network upgrades
| MOU update | The ISO, California Energy Commission (CEC), California Public Utilities Commission (CPUC) updated a Memorandum of Understanding in 2022 that tightened the linkages between demand forecasting, resource planning, and transmission planning. Recent legislation requires the parties to review and update the MOU by January 2028.
Large Load Interconnection and Study
| Order to Show Cause 205 filing | Responds to the Federal Energy Regulatory Commission (FERC) Order to Show Cause on Large Loads and describes areas where ISO leadership and engagement is necessary to enable innovation while protecting customers and ensuring safe and reliable service
| Consideration of permanent flexible interconnection and proximate loads | Future consideration of a flexible load interconnection service offering that would be permanent in order to avoid network upgrades.
| Consideration of large load curtailment for risk mitigation | Explore a risk mitigation tool for capacity constraints associated with large load growth.Stakeholders would work with the ISO to develop a framework for curtailing large loads under tight grid conditions, before a reliability event.
Interconnection Process Enhancements
| IPE 6.0 (Prior to Cluster 17) | Interconnection process enhancements to apply to Cluster 17 (2027)
| IPE 7.0 (if needed) | Interconnection process enhancements to apply to Cluster 18 (2028)
| IPE 8.0 (if needed) | Interconnection process enhancements to apply to Cluster 19 (2029)
Resource Adequacy Modeling and Program Design |  | Collaborate with stakeholders on enhancements to the ISO's Resource Adequacy program amid an evolving generation mix, variable supply conditions, and changes to resource planning frameworks in California and the West.
| Track 5: MIC enhancements | Enhancement to the allocation and transactability of Maximum Import Capability (MIC) to provide longer term certainty for LSEs and resource developers.
Compensation for reactive power from IBRs outside of specified range |  | Consider possible compensation for IBR facilities providing additional reactive power in excess of the required LGIA requirements.