## Roadmap
September 24, 2026
2027-2029 California ISO Market Policy Initiatives Roadmap
|  | 2026 | 2027 |  |  |  | 2028 |  |  |  | 2029
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Commitment Cost Bidding Flexibility |  | 2026 Q4: Public dialogue: next steps; 2028 Q1: Implementation
Congestion Revenue Rights Enhancements
| Phase 1: Loop flow modeling | 2026 Q4: Implementation; 2027 Q1: Complete
| Phase 2a: Modeling enhancements | 2026 Q4: Policy development; 2027 Q1: Policy development; 2027 Q2: Implementation
Decision
| Phase 2b: Product definition and CRR auction & allocation process enhancements | 2026 Q4: Policy development; 2027 Q3: Decision; 2027 Q4: Implementation
Demand and Distributed Energy Market Integration
| Track 1: End-user exports in demand response performance measurement | 2026 Q4: Policy development; 2027 Q3: Decision; 2028 Q1: Implementation
| Track 2: Demand flexibility enhancements | 2026 Q4: Policy development; 2027 Q3: Decision
| Track 3: Large load forecasting enhancements | 2027 Q1: Policy development; 2027 Q4: Decision
EDAM Congestion Revenue Allocation |  | 2026 Q4: Policy development; 2027 Q3: Decision; 2027 Q4: Implementation
EDAM Enhancements |  | 2026 Q4: As needed
Intertie Schedule Modeling Enhancements |  | 2026 Q4: Policy development; 2027 Q4: Decision; 2028 Q1: Implementation
Gas Resource Management |  | 2026 Q4: Implementation
Greenhouse Gas Coordination
| Accounting and reporting | 2026 Q4: Implementation
| Net export constraint | 2027 Q1: Public dialogue: next steps
| Washington and California program linkage | 2027 Q1: Policy development
Price Formation Enhancements
| Comprehensive scarcity pricing & market power mitigation | 2026 Q4: Policy development; 2027 Q4: Decision; 2028 Q3: Implementation
| Fast start pricing | 2026 Q4: Postponed; 2027 Q1: Public dialogue: next steps
Resource Adequacy Modeling and Program Design
| Track 1: Modeling and default rules | 2026 Q4: Implementation
| Track 2: Outage substitution and availability and incentive mechanisms | 2026 Q4: Policy development; 2027 Q1: Decision; 2028 Q1: Implementation
| Track 3a: Resource visibility | 2026 Q4: Implementation
| Track 3b: Backstop reform and long-term EDAM RSE solutions | 2026 Q4: Policy development; 2027 Q4: Decision; 2028 Q1: Implementation
| Track 4: Flex RA | 2027 Q1: Policy development
| Track 5: MIC enhancements | 2026 Q4: Policy development; 2027 Q3: Decision
Seams |  | 2027 Q1: As needed
Storage Design and Modeling
| Topic group 1: Outage management enhancements | 2026 Q4: Implementation
| Topic group 2: Uplift & default energy bids | 2026 Q4: Policy development; 2027 Q1: Decision; 2027 Q2: Implementation
| Topic group 3: State-of-charge management | 2026 Q4: Policy development; 2027 Q2: Decision; 2027 Q4: Implementation
| Topic group 4: Mixed-fuel & distribution-level resources | 2026 Q4: Policy development; 2027 Q1: BPM change; 2027 Q2: Implementation
Variable Operations and Maintenance Cost: Triennial Review |  | 2026 Q4: Decision; 2027 Q1: Implementation
Virtual Bidding for EDAM BAAs |  | 2028 Q1: Policy development
WEIM Resource Sufficiency Evaluation Enhancements |  | 2026 Q4: Postponed; 2027 Q1: As needed
NOTE: All implementation dates listed are "no sooner than"
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anja to confirm Q3 or Q4 - have seen both used
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved from q3 to q4
Note on H42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per AB: consider starting mid-2027, discuss w Anna. Process will take ~1 year. Requiring BAs to take on virtual bidding...how much onramp do they need?

## Initiative Descriptions
Initiative Descriptions
Commitment Cost Bidding Flexibility |  | Evaluate implementation of policy approved by the ISO Board in 2018, with advisory approval from the WEIM Governing Body. This evaluation will focus on one part of this initiative (Commitment Cost Default Energy Bid Enhancements) which establishes dynamic commitment cost mitigation. This work supports gas resource management.
Congestion Revenue Rights Enhancements
| Phase 1: Loop flow modeling | Enhanced loop flow modeling in the annual CRR process.
| Phase 2a: Modeling enhancements | Build on Phase 1 work seeking enhancements to address modeling issues impacting revenue adequacy.
| Phase 2b: Product definition and CRR auction & allocation process enhancements | (1) Product definition: Pursue stakeholder-identified reforms to the CRR product definition to align with participant hedging use. (2) CRR auction & allocation process enhancements: Seek a comprehensive set of solutions to meet participant hedging needs and equity concerns stakeholders have identified from persistent differences between the CRR auction and DA market congestion values.
Demand and Distributed Energy Market Integration |  | Refine participation models and market rules facilitating the representation of demand and distributed energy, independently or managed in aggregation, in the day-ahead and real-time California ISO markets.
| Track 1: End-user exports in demand response performance measurement | Track 1 focuses on allowing customer-level exports from behind-the-meter resources to count toward demand response performance, while maintaining an aggregate resource-level export limit so PDR/RDRR remain load-curtailment resources.
| Track 2: Demand flexibility enhancements | Track 2 explores broader demand flexibility enhancements, including adapting DR participation for WEIM/EDAM, participation pathways for large loads, and potential reliability DR modifications.
| Track 3: Large load forecasting enhancements | Track 3 focuses on establishing a consistent framework for how large loads are represented in CAISO’s short-term demand forecasting and in operations, including defining what constitutes a large load as well as establishing associated forecasting, data, and operational requirements. The initiative would also establish clear criteria and requirements for non-conforming load.
EDAM Congestion Revenue Allocation |  | Develop a long-term, durable design for allocating congestion revenues among balancing areas participating in the Extended Day-Ahead Market. This design builds on the transitional EDAM CRA design which allocates a portion of day-ahead parallel flow congestion revenues to the EDAM balancing area where market participants have paid prices that include those congestion costs, rather than to the balancing area where the constraint occurs.
EDAM Enhancements |  | Reserves policy resources for issues related to EDAM implementation as necessary.
Intertie Schedule Modeling Enhancements |  | Consider evolution of the design for modeling intertie schedules for the CAISO balancing area.
Gas Resource Management |  | Near-term enhancements to the ISO's market rules and processes that will improve functionality for regional market participants with natural gas-fired resources. These enhancements include: (1) Changes to day-ahead advisory market runs to improve fuel procurement forecasts available within gas nomination timelines. (2) Additional options for cost inputs, adjustments, and recovery to better accommodate unique supply arrangements and exceptional circumstances such as extreme weather. (3) Additional options for managing a resource's gas system limitations.
Greenhouse Gas Coordination |  | Evolve the design of a greenhouse gas (GHG) emissions accounting report available to market participants to support compliance with state, local, or corporate GHG reduction targets.
| Accounting and reporting | The approach overlays ownership and contract data with market dispatch results to produce data that allow reporting entities to see and understand the emissions intensity of their portfolio. This data increases the transparency of GHG emissions generated in the Western Energy Imbalance Market and Extended Day Ahead Market footprint.
| Net export constraint | FERC approved delaying implementation of this approved policy which would have augmented the market design to reduce the potential for emissions leakage resulting from day-ahead market and real-time market transfers into California balancing authority areas. Assess implementation of the GHG net export constraint with production data, and work with stakeholders to deploy this constraint effectively without the risk of creating anomalous results
| Washington and California program linkage | Stakeholder initiative to determine whether market design changes are necessary for greenhouse gas bidding under Washington and California program linkage
Price Formation Enhancements
| Comprehensive scarcity pricing and market power mitigation | Enhance price formation in the California ISO markets to reduce unnecessary mitigation, better reflect system stress in market prices, strengthen reliability signals, and provide consistent incentives across the Western Energy Imbalance Market and Extended Day Ahead Market.
| Fast start pricing | Explore approaches to integrating commitment costs of fast start resources into market prices to better reflect the incremental cost of serving load.
Resource Adequacy Modeling and Program Design |  | Collaborate with stakeholders on enhancements to the ISO's Resource Adequacy program amid an evolving generation mix, variable supply conditions, and changes to resource planning frameworks in California and the West.
| Track 1: Modeling and default rules | Update the ISO's default methodologies for qualifying capacity and planning reserve margin, creating a set of resource adequacy rules that strengthen system reliability while maintaining the autonomy of local regulatory authorities. The framework serves as a default set of RA resources in cases where a local regulatory authority has not established its own methodology.
| Track 2: Outage substitution and availability and incentive mechanisms | Aims to improve CAISO’s current availability incentive mechanism by aligning performance expectations with evolving resource adequacy needs.
| Track 3a: Resource visibility | Enhance the ISO's resource adequacy processes by improving visibility into resources available for procurement through the ISO's backstop measures. Obtaining this information will better inform the ISO's Capacity Procurement Mechanism processes and is a first step in a multi-phase effort to enhance the effectiveness of the ISO's backstop processes.
| Track 3b: Backstop reform and long-term EDAM RSE solutions | Conduct a structural review and explore potential reform of the backstop programs. Explore Capacity Procurement Mechanism (CPM) reforms, including: (1) Soft offer cap methodology (2) Changes to how CPM need is assessed (3) Changes to the CPM designations in line with need assessment changes Develop EDAM Resource Sufficiency Evaluation post-launch improvements, including: (1) Causation-based cost allocation methodology for the RSE failure surcharge (2) 9am bidding and alternatives to exceptional dispatch for addressing potential shortfalls
| Track 4: Flex RA | Comprehensive reevaluation of CAISO Flex RA program in light of stakeholder feedback and changing reliability needs.
| Track 5: MIC enhancements | Enhancement to the allocation and transactability of Maximum Import Capability MIC) to provide longer term certainty for LSEs and resource developers.
Seams |  | Market design initiatives that are narrowly scoped to address market seams issues that require tariff changes or filings at the Federal Energy Regulatory Commission.
Storage Design and Modeling |  | Note: Some topics under this effort may not be decisional items. Explore enhancements to energy storage market design, modeling, and processes. Efforts are organized into four topic groups: (1) Outage management: Enhance ISO business practices and systems to better reflect the unique characteristics of battery storage resources and their impacts on outages and operational capabilities. (2) Uplift and Default Energy Bids: Reform energy storage bid cost recovery provisions and default energy bids. Bid cost recovery, also referred to as uplift, is the additional payment to resources to ensure compensation for applicable costs when the revenues from following market dispatch are insufficient. Default energy bids are previously agreed upon bids that the ISO may use to limit the ability of local market power to affect market outcomes. (3) State-of-Charge management: Consider enhancements to the tools available to scheduling coordinators and the ISO to manage the state-of-charge of storage resources. (4) Mixed fuel and distribution-level resources: Improve ISO business and modeling practices regarding mixed-fuel configurations. Mixed-fuel configurations are generation facilities with multiple technologies, participating as a hybrid resource or co-located resources.
Variable Operations & Maintenance Cost Review |  | Update default variable operations and maintenance cost adders to reflect inflation since the 2023 review. Establish a default variable operations cost for energy storage resources.
Virtual Bidding for EDAM BAAs |  | This initiative would identify conditions under which an EDAM BAA would be required to accept virtual bids. Virtual bidding allows financial participants to converge day-ahead and 15-minute prices in two cases which might otherwise result in inefficient market outcomes or allow manipulation: (1): under-scheduling of load in the day-ahead market and (2): consistently different GHG prices in the DA and RT driven by differences in the GHG footprints or physical withholding. The EDAM GHG policy will also be considering allowing virtual supply to bid GHG.
WEIM Resource Sufficiency Evaluation Enhancements |  | Examine unresolved policy from the RSEE Phase 2 effort, including the expansion and refinement of the Assistance Energy Transfer product, the interplay between the hour-ahead scheduling process and the base scheduling process, and e-tagging rules associated with market awards. The initiative would also explore the policy implications of stakeholder suggestions such as an expansion of a de minimis failure deadband and the forecasting methodologies associated with uncertainty-related outputs.