## Roadmap
June 23, 2026
2026 Revised California ISO Market Policy Initiatives Roadmap
2026
|  | Q1 | Q2 | Q3 | Q4
Commitment Cost Bidding Flexibility |  | Public dialogue: next steps
Congestion Revenue Rights Enhancements
| Phase 1: Enhanced loop flow modeling | Policy development |  | Decision | Implementation
| Phase 2: Further enhancements | Policy development
Demand and Distributed Energy Market Integration |  | Policy development |  | Decision | Implementation
Policy development
EDAM Congestion Revenue Allocation |  | Policy development
EDAM Enhancements |  | As needed
Intertie Schedule Modeling Enhancements |  |  | Policy development
Finance Enhancements |  | Policy development | Decision
Gas Resource Management |  |  |  | Implementation
Greenhouse Gas Coordination |  |  |  | Implementation
Price Formation Enhancements
| Scarcity pricing & market power mitigation | Policy development |  |  | Decision
| Fast start pricing | Postponed
Resource Adequacy Modeling and Program Design
| Track 1: Modeling and default rules |  | Implementation
| Track 2: Outage substitution and availability and incentive mechanisms | Policy development |  |  | Decision
| Track 3a: Resource visibility |  |  |  | Implementation
| Track 3b: Backstop reform and long-term EDAM RSE solutions |  |  |  | Policy development
Storage Design and Modeling
| Topic group 1: Outage management enhancements | Policy development |  | Implementation
| Topic group 2: Uplift & default energy bids | Policy development
| Topic group 3: State-of-charge management | Policy development
| Topic group 4: Mixed-fuel & distribution-level resources | Policy development
Variable Operations and Maintenance Cost: Triennial Review |  |  | Policy development |  | Decision
Implementation
WEIM Resource Sufficiency Evaluation Enhancements |  | Postponed

## Initiative Descriptions
Initiative Descriptions
Commitment Cost Bidding Flexibility |  | Evaluate implementation of policy approved by the ISO Board in 2018, with advisory approval from the WEIM Governing Body. This evaluation will focus on one part of this initiative (Commitment Cost Default Energy Bid Enhancements) which establishes dynamic commitment cost mitigation. This work supports gas resource management.
Congestion Revenue Rights Enhancements |  | Enhance the ISO's Congestion Revenue Rights market using a working group structure to identify goals and problem statements that will lead into development of policy solutions. Working groups are exploring topics including issues related to auction efficiency, revenue inadequacy, product definition, and allocation. Working groups are also reviewing the historical goals of CRRs and the current processes for the allocation and auction of CRRs.
| Phase 1: Enhanced loop flow modeling | Enhanced loop flow modeling in the annual CRR process.
| Phase 2: Further enhancements | Comprehensively consider broad structural enhancements and redesigns including, among other topics, addressing auction efficiency through the minimum bid/price floor, updating the product definition, and improving the effectiveness of the allocation.
Demand and Distributed Energy Market Integration |  | Refine participation models and market rules facilitating the representation of demand and distributed energy, independently or managed in aggregation, in the day-ahead and real-time California ISO markets. Six theme areas include: (1) Performance evaluation methodologies (2) Proxy Demand Response economic participation model enhancements (3) Reliability Demand Response Resource participation model (4) Distributed Energy Resource participation (5) Expanding demand side bidding options (6) Enhancing demand flexibility market optimization options
EDAM Congestion Revenue Allocation |  | Develop a long-term, durable design for allocating congestion revenues among balancing areas participating in the Extended Day-Ahead Market. This design builds on the transitional EDAM CRA design which allocates a portion of day-ahead parallel flow congestion revenues to the EDAM balancing area where market participants have paid prices that include those congestion costs, rather than to the balancing area where the constraint occurs.
EDAM Enhancements |  | Reserves policy resources for issues related to EDAM implementation as necessary.
Intertie Schedule Modeling Enhancements |  | Consider evolution of the design for modeling intertie schedules for the CAISO balancing area.
Finance Enhancements |  | Address several finance-related topics, including: (1) Next cost-of-service study delay (2) 2027-2028 revenue requirement cap increase (3) Other revenue requirements or finance enhancements as necessary
Gas Resource Management |  | Near-term enhancements to the ISO's market rules and processes that will improve functionality for regional market participants with natural gas-fired resources. These enhancements include: (1) Changes to day-ahead advisory market runs to improve fuel procurement forecasts available within gas nomination timelines. (2) Additional options for cost inputs, adjustments, and recovery to better accommodate unique supply arrangements and exceptional circumstances such as extreme weather. (3) Additional options for managing a resource's gas system limitations.
Greenhouse Gas Coordination |  | Evolve the design of a greenhouse gas (GHG) emissions accounting report available to market participants to support compliance with state, local, or corporate GHG reduction targets. The approach overlays ownership and contract data with market dispatch results to produce data that allow reporting entities to see and understand the emissions intensity of their portfolio. This data increases the transparency of GHG emissions generated in the Western Energy Imbalance Market and Extended Day Ahead Market footprint.
Price Formation Enhancements
| Scarcity pricing & market power mitigation | Enhance price formation in the California ISO markets to reduce unnecessary mitigation, better reflect system stress in market prices, strengthen reliability signals, and provide consistent incentives across the Western Energy Imbalance Market and Extended Day Ahead Market.
| Fast start pricing | Explore approaches to integrating commitment costs of fast start resources into market prices to better reflect the incremental cost of serving load.
Resource Adequacy Modeling and Program Design |  | Collaborate with stakeholders on enhancements to the ISO's Resource Adequacy program amid an evolving generation mix, variable supply conditions, and changes to resource planning frameworks in California and the West.
| Track 1: Modeling and default rules | Update the ISO's default methodologies for qualifying capacity and planning reserve margin, creating a set of resource adequacy rules that strengthen system reliability while maintaining the autonomy of local regulatory authorities. The framework serves as a default set of RA resources in cases where a local regulatory authority has not established its own methodology.
| Track 2: Outage & substitution and availability and incentive mechanisms | Aims to improve CAISO’s current availability incentive mechanism by aligning performance expectations with evolving resource adequacy needs.
| Track 3a: Resource visibility | Enhance the ISO's resource adequacy processes by improving visibility into resources available for procurement through the ISO's backstop measures. Obtaining this information will better inform the ISO's Capacity Procurement Mechanism processes and is a first step in a multi-phase effort to enhance the effectiveness of the ISO's backstop processes.
| Track 3b: Backstop reform and long-term EDAM RSE solutions | Conduct a structural review and explore potential reform of the backstop programs. Explore Capacity Procurement Mechanism (CPM) reforms, including: (1) Soft offer cap methodology (2) Changes to how CPM need is assessed (3) Changes to the CPM designations in line with need assessment changes Develop EDAM Resource Sufficiency Evaluation post-launch improvements, including: (1) Causation-based cost allocation methodology for the RSE failure surcharge (2) 9am bidding and alternatives to exceptional dispatch for addressing potential shortfalls
Storage Design and Modeling |  | Note: Some topics under this effort may not be decisional items and could be finalized ahead of the described timeline. Explore enhancements to energy storage market design, modeling, and processes. Efforts are organized into four topic groups: (1) Outage management (2) Uplift and Default Energy Bids (3) State-of-Charge management (4) Mixed fuel and distribution-level resources
Variable Operations & Maintenance Cost Review |  | In 2026, the ISO is conducting its triennial review of default variable operations and maintenance (VOM) adder values. The ISO committed to review default VOM adder values once every three years, with the last review being in 2023. This policy initiative will also consider whether to expand the review to include batteries’ variable storage operations cost (VSOC).
WEIM Resource Sufficiency Evaluation Enhancements |  | Examine unresolved policy from the RSEE Phase 2 effort, including the expansion and refinement of the Assistance Energy Transfer product, the interplay between the hour-ahead scheduling process and the base scheduling process, and e-tagging rules associated with market awards. The initiative would also explore the policy implications of stakeholder suggestions such as an expansion of a de minimis failure deadband and the forecasting methodologies associated with uncertainty-related outputs.